## Issue Log
Issue Tracker Template
Date
# | Issue | Priority | Open | Close | Comments
1 | User name check fails | Low | 2009-07-12 | 2009-07-15
2 | Password field is not mandatory | Medium | 2009-07-12 | 2009-07-13
3 | Reset button doesn’t work | High | 2009-07-14 | 2009-07-19
4 | When window is maximized, the layout is compromised | Low | 2009-07-15 | 2009-07-16
5 | Password field takes more than 99 chars | Medium | 2009-07-15 | 2009-07-18
6 | User name allows SQL injection | Medium | 2009-07-15 | 2009-07-20
7 | Password allows SQL injection | Low | 2009-07-15 | 2009-07-22
8 | User name allows HTML Injection | High | 2009-07-16 | 2009-07-20
9 | Password allows HTML Injection | Low | 2009-07-16 | 2009-07-17
10 | Submit doesn’t work on enter | Medium | 2009-07-18 | 2009-07-25
11 | User name is not the default field on screen load | High | 2009-07-18 | 2009-07-24
12 | When hitting F5, the error message still remains | Low | 2009-07-18 | 2009-07-25
13 | Message is wrong | Medium | 2009-07-22 | 2009-07-24
14 | User name check fails | Medium | 2009-07-23 | 2009-07-28
15 | Password field is not mandatory | Low | 2009-07-23 | 2009-07-27
16 | Reset button doesn’t work | High | 2009-07-23 | 2009-07-30
17 | When window is maximized, the layout is compromised | Medium | 2009-07-23 | 2009-07-25
18 | Password field takes more than 99 chars | High | 2009-07-23 | 2009-07-28
19 | User name allows SQL injection | Low | 2009-07-24 | 2009-07-31
20 | Password allows SQL injection | Medium | 2009-07-24 | 2009-07-30
21 | User name allows HTML Injection | Medium | 2009-07-24 | 2009-07-30
22 | Password allows HTML Injection | Low | 2009-07-27 | 2009-08-02
23 | Submit doesn’t work on enter | High | 2009-07-28 | 2009-07-29
24 | User name is not the default field on screen load | Low | 2009-07-29 | 2009-08-02
25 | When hitting F5, the error message still remains | Medium | 2009-07-31 | 2009-08-07
26 | Message is wrong | High | 2009-08-01 | 2009-08-04
27 | User name check fails | Low | 2009-08-01 | 2009-08-05
28 | Password field is not mandatory | Medium | 2009-08-02 | 2009-08-09
29 | Reset button doesn’t work | Medium | 2009-08-04 | 2009-08-05
30 | When window is maximized, the layout is compromised | Medium | 2009-08-05 | 2009-08-12
31 | Password field takes more than 99 chars | High | 2009-08-05 | 2009-08-07
32 | User name allows SQL injection | Low | 2009-08-06 | 2009-08-09
33 | Password allows SQL injection | Medium | 2009-08-07 | 2009-08-09
34 | User name allows HTML Injection | Medium | 2009-08-07 | 2009-08-08
35 | Password allows HTML Injection | Low | 2009-08-10 | 2009-08-16
36 | Submit doesn’t work on enter | High | 2009-08-12 | 2009-08-19
37 | User name is not the default field on screen load | Low | 2009-08-14 | 2009-08-17
38 | When hitting F5, the error message still remains | Medium | 2009-08-15 | 2009-08-21
39 | Message is wrong | High | 2009-08-17 | 2009-08-24
40 | User name check fails | Low | 2009-08-18 | 2009-08-25
41 | Password field is not mandatory | Medium | 2009-08-21 | 2009-08-25
42 | Reset button doesn’t work | Medium | 2009-08-22 | 2009-08-27
43 | When window is maximized, the layout is compromised | High | 2009-08-22 | 2009-08-25
44 | Password field takes more than 99 chars | Low | 2009-08-22 | 2009-08-28
45 | User name allows SQL injection | Medium | 2009-08-22 | 2009-08-24
46 | Password allows SQL injection | High | 2009-08-24 | 2009-08-30
47 | User name allows HTML Injection | Low | 2009-08-24 | 2009-08-27
48 | Password allows HTML Injection | Medium | 2009-08-27
49 | Submit doesn’t work on enter | Medium | 2009-08-27
50 | User name is not the default field on screen load | Medium | 2009-08-29
51 | When hitting F5, the error message still remains | High | 2009-08-29
52 | Message is wrong | Low | 2009-08-29
53 | User name check fails | Medium | 2009-08-31
54 | Password field is not mandatory | Medium | 2009-09-01
55 | Reset button doesn’t work | Low | 2009-09-03
56 | When window is maximized, the layout is compromised | High | 2009-09-04
57 | Password field takes more than 99 chars | Low | 2009-09-05
58 | User name allows SQL injection | Medium | 2009-09-06
59 | Password allows SQL injection | High | 2009-09-07
60 | User name allows HTML Injection | Low | 2009-09-07
Twitter, Chirp, Chirp
Visit the Blog
E-Mail Newsletter
RSS

## Issue Tracker Chart
Open vs. Closed Issues in a Chart
Start Date: |  | 2009-09-08
Issues Opened and Closed in Last 30 days
Date | Total Opened | Total Closed
2009-08-10 | 1 | 0
2009-08-11 | 1 | 0
2009-08-12 | 2 | 1
2009-08-13 | 2 | 1
2009-08-14 | 3 | 1
2009-08-15 | 4 | 1
2009-08-16 | 4 | 2
2009-08-17 | 5 | 3
2009-08-18 | 6 | 3
2009-08-19 | 6 | 4 | Total Outstanding Issues
2009-08-20 | 6 | 4
2009-08-21 | 7 | 5 | 3 High | 6 Medium | 4 Low
2009-08-22 | 11 | 5
2009-08-23 | 11 | 5
2009-08-24 | 13 | 7
2009-08-25 | 13 | 10
2009-08-26 | 13 | 10
2009-08-27 | 15 | 12
2009-08-28 | 15 | 13
2009-08-29 | 18 | 13
2009-08-30 | 18 | 14
2009-08-31 | 19 | 14
2009-09-01 | 20 | 14
2009-09-02 | 20 | 14
2009-09-03 | 21 | 14
2009-09-04 | 22 | 14
2009-09-05 | 23 | 14
2009-09-06 | 24 | 14
2009-09-07 | 26 | 14
2009-09-08 | 26 | 14
Formulas:
Date = D3-30+ROWS(B7:[Date])
Twitter, Chirp, Chirp
Visit the Blog
E-Mail Newsletter
RSS

## Issue Log 2
Issue Tracker Template
# | Issue | Type of Issue | Priority | Open Date | Open By | Close Date | Close By | Comments
1 | User name check fails | Error | Low | 2009-07-12 | John | 2009-07-15 | Bill
2 | Password field is not mandatory | Error | Medium | 2009-07-12 | Arun | 2009-07-13 | Bill
3 | Reset button doesn’t work | Error | High | 2009-07-14 | Martha | 2009-07-19 | Jon
4 | When window is maximized, the layout is compromised | Question | Low | 2009-07-15 | Benji | 2009-07-16 | Gopal
5 | Password field takes more than 99 chars | Change | Medium | 2009-07-15 | Anita | 2009-07-18 | Smith
6 | User name allows SQL injection | Error | Medium | 2009-07-15 | Anita | 2009-07-20 | Smith
7 | Password allows SQL injection | Error | Low | 2009-07-15 | Anita | 2009-07-22 | Gopal
8 | User name allows HTML Injection | Error | High | 2009-07-16 |  | 2009-07-20
9 | Password allows HTML Injection | Error | Low | 2009-07-16 |  | 2009-07-17
10 | Submit doesn’t work on enter | Question | Medium | 2009-07-18 |  | 2009-07-25
11 | User name is not the default field on screen load | Change | High | 2009-07-18 |  | 2009-07-24
12 | When hitting F5, the error message still remains | Error | Low | 2009-07-18 |  | 2009-07-25
13 | Message is wrong | Error | Medium | 2009-07-22 |  | 2009-07-24
14 | User name check fails | Error | Medium | 2009-07-23 |  | 2009-07-28
15 | Password field is not mandatory | Error | Low | 2009-07-23 |  | 2009-07-27
16 | Reset button doesn’t work | Question | High | 2009-07-23 |  | 2009-07-30
17 | When window is maximized, the layout is compromised | Change | Medium | 2009-07-23 |  | 2009-07-25
18 | Password field takes more than 99 chars | Error | High | 2009-07-23 |  | 2009-07-28
19 | User name allows SQL injection | Error | Low | 2009-07-24 |  | 2009-07-31
20 | Password allows SQL injection | Error | Medium | 2009-07-24 |  | 2009-07-30
21 | User name allows HTML Injection | Error | Medium | 2009-07-24 |  | 2009-07-30
22 | Password allows HTML Injection | Question | Low | 2009-07-27 |  | 2009-08-02
23 | Submit doesn’t work on enter | Change | High | 2009-07-28 |  | 2009-07-29
24 | User name is not the default field on screen load | Error | Low | 2009-07-29 |  | 2009-08-02
25 | When hitting F5, the error message still remains | Risk | Medium | 2009-07-31 |  | 2009-08-07
26 | Message is wrong | Others | High | 2009-08-01 |  | 2009-08-04
27 | User name check fails | Error | Low | 2009-08-01 |  | 2009-08-05
28 | Password field is not mandatory | Error | Medium | 2009-08-02 |  | 2009-08-09
29 | Reset button doesn’t work | Error | Medium | 2009-08-04 |  | 2009-08-05
30 | When window is maximized, the layout is compromised | Question | Medium | 2009-08-05 |  | 2009-08-12
31 | Password field takes more than 99 chars | Change | High | 2009-08-05 |  | 2009-08-07
32 | User name allows SQL injection | Error | Low | 2009-08-06 |  | 2009-08-09
33 | Password allows SQL injection | Risk | Medium | 2009-08-07 |  | 2009-08-09
34 | User name allows HTML Injection | Others | Medium | 2009-08-07 |  | 2009-08-08
35 | Password allows HTML Injection | Error | Low | 2009-08-10 |  | 2009-08-16
36 | Submit doesn’t work on enter | Error | High | 2009-08-12 |  | 2009-08-19
37 | User name is not the default field on screen load | Error | Low | 2009-08-14 |  | 2009-08-17
38 | When hitting F5, the error message still remains | Question | Medium | 2009-08-15 |  | 2009-08-21
39 | Message is wrong | Change | High | 2009-08-17 |  | 2009-08-24
40 | User name check fails | Error | Low | 2009-08-18 |  | 2009-08-25
41 | Password field is not mandatory | Risk | Medium | 2009-08-21 |  | 2009-08-25
42 | Reset button doesn’t work | Others | Medium | 2009-08-22 |  | 2009-08-27
43 | When window is maximized, the layout is compromised | Question | High | 2009-08-22 |  | 2009-08-25
44 | Password field takes more than 99 chars | Change | Low | 2009-08-22 |  | 2009-08-28
45 | User name allows SQL injection | Error | Medium | 2009-08-22 |  | 2009-08-24
46 | Password allows SQL injection | Error | High | 2009-08-24 |  | 2009-08-30
47 | User name allows HTML Injection | Error | Low | 2009-08-24 |  | 2009-08-27
48 | Password allows HTML Injection | Error | Medium | 2009-08-27
49 | Submit doesn’t work on enter | Question | Medium | 2009-08-27
50 | User name is not the default field on screen load | Change | Medium | 2009-08-29
51 | When hitting F5, the error message still remains | Error | High | 2009-08-29
52 | Message is wrong | Error | Low | 2009-08-29
53 | User name check fails | Error | Medium | 2009-08-31
54 | Password field is not mandatory | Error | Medium | 2009-09-01
55 | Reset button doesn’t work | Question | Low | 2009-09-03
56 | When window is maximized, the layout is compromised | Change | High | 2009-09-04
57 | Password field takes more than 99 chars | Error | Low | 2009-09-05
58 | User name allows SQL injection | Risk | Medium | 2009-09-06
59 | Password allows SQL injection | Others | High | 2009-09-07
60 | User name allows HTML Injection | Error | Low | 2009-09-07
Twitter, Chirp, Chirp
Visit the Blog
E-Mail Newsletter
RSS